## System Mapping
Mapping ID | Source System | Source Classification | Source Data Objects / Capabilities | Target System(s) | Target Classification(s) | Migration Intent | Migration Method | IT Owner | Business Owner | Batch Participation | MML / Coexistence Dependency | Key Dependencies | Status | Open Issues / Notes
MAP-001 | Optima | Legacy source | Customer, billing, CRM, mobile account/service data | ["Kenan 7", "MDM", "Possibly other target systems TBD"] | ["Target Billing", "Target Master Data", "TBD"] | Core source extraction and transformation | TBD | Amdocs / TBD | TBD | Yes, likely | Yes, likely for coexistence/routing | Target schemas not fully confirmed | In Progress | Broad source system; requires decomposition by domain
MAP-002 | Kenan 5 | Legacy source | Billing data | ["Kenan 7"] | ["Target Billing"] | Billing migration | Full extract / import | Amdocs / TBD | TBD | Yes | No clear dependency stated | Kenan 7 readiness | In Progress | Discussed as familiar but still complex
MAP-003 | Altice Labs | Legacy source | Mobile/network/service/inventory-related data (exact scope unclear) | ["UID / Inventory", "Service Inventory", "Possibly SIM Inventory TBD"] | ["Target Inventory", "Target Service Inventory", "TBD"] | Partial migration or recreation | TBD | TBD | TBD | Yes, possible | Possibly | Need SME confirmation on exact data set | Open | Scope explicitly uncertain in meeting
MAP-004 | Logical Doc | Legacy source | Documents / document references | ["Document Management"] | ["Target Document Repository"] | Historical document migration | TBD | TBD | TBD | Possibly | No clear dependency stated | Mapping logic from current model | Open | Valery said Logical Doc is a migration item
MAP-005 | Couchbase | Legacy source | Customer/document linkage, document IDs/links | ["Document Management", "Possibly supporting mapping layer TBD"] | ["Target Document Repository", "TBD"] | Reconstruct linkage/mapping in target state | TBD | TBD | TBD | Possibly | Possibly indirect | Need design for preserving customer-to-document relationship | Open | Current linkage model is complex
MAP-006 | Vindicia | Legacy source | Recurring payment profiles | ["Payment Portal", "Chase", "PaymentTech"] | ["Target Payment Layer", "Target Processor", "Target Processor"] | Payment profile copy or migration | Evaluate copy-in-advance approach | TBD | TBD | Yes | Possibly no direct MML dependency | Payment tokenization feasibility | Open | Advance copy into dormant state discussed
MAP-007 | Kansas | Retained legacy / source | Historical usage records | ["New BSS TBD", "Possibly Kenan 7 TBD", "Possibly no migration / retained only"] | ["TBD", "TBD", "Retained Legacy"] | Possible limited carryover or retention only | TBD | TBD | TBD | Unclear | No clear dependency stated | Need usage-scope decision | Open | Sebastian suggested history may remain there
MAP-008 | Nokia Usage App | Legacy source | Usage summaries | ["New BSS TBD"] | ["TBD"] | Possibly support statement/usage display continuity | TBD | TBD | TBD | Unclear | No clear dependency stated | Clarify whether summary data must move | Open | Referenced only briefly
MAP-009 | Current IVR / legacy routing | Transitional source | Current routing decision logic for old vs new stack | ["MML", "CES", "Cisco", "OneView"] | ["Coexistence Control", "Target Contact Center", "Target Contact Center", "Target Orchestration"] | Transitional routing support during coexistence | TBD | TBD | TBD | Yes | Yes | MML design and target routing approach | Open | Decision point appears to happen in IVR today
MAP-010 | Legacy payment/risk flow (incl. possible Cybersource role) | Legacy/transitional | Payment transaction risk checks | ["Payment Portal", "Chase", "PaymentTech", "Possibly Cybersource TBD"] | ["Target Payment", "Target Processor", "Target Processor", "Unclear"] | Payment flow continuity | TBD | TBD | TBD | Yes, for active migration cutover | No clear dependency stated | Final target payment/risk architecture unclear | Open | Cybersource may disappear

## Source Data
Domain ID | Source Domain | Primary Source System | Source Object Examples | Target System(s) | Target Object Examples | Required in Micro-Batch? | Historical Migration? | Active-State Migration? | IT Owner | Business Owner | Notes / Open Questions
DOM-001 | Customer Master | Optima | Customer profile, identifiers | ["MDM", "Kenan 7"] | ["Customer Master", "Billing Customer"] | Yes | Yes | Yes | TBD | TBD | Major migration domain
DOM-002 | Billing Account | Kenan 5 / Optima | Account, bill profile, account relationships | ["Kenan 7"] | ["Billing Account"] | Yes | Yes | Yes | TBD | TBD | Core billing migration
DOM-003 | Subscription / Product | Optima | Mobile subscription, plans, product relationships | ["Kenan 7", "Product Inventory", "Possibly MDM TBD"] | ["Subscription", "Product Holding", "Customer Product View"] | Yes | Likely | Yes | TBD | TBD | Need target system-of-record clarity
DOM-004 | Service / Service Inventory | Altice Labs, Optima | Service states, provisioning-related items | ["UIV / Inventory", "Service Inventory", "One OSS-related stores"] | ["Service Instance", "Inventory Object"] | Yes, likely | Possibly partial | Yes | TBD | TBD | Scope unclear
DOM-005 | Device / SIM | Altice Labs, current inventory flows | SIM, device association, IMEI linkage | ["SIM Inventory", "UIV / Inventory", "Assurance"] | ["SIM", "Device", "Coverage / insurance association"] | Yes | Partial / unclear | Yes | TBD | TBD | New SIMs may be created instead of migrated
DOM-006 | MSISDN / Numbering | Legacy BSS + network-side systems | Mobile number / portability state | ["Portability", "Target Network Flows", "New BSS"] | ["Ported Number", "Subscription Identifier"] | Yes | No clear historical migration stated | Yes | TBD | TBD | Strong network dependency
DOM-007 | Documents / Consents | Logical Doc, Couchbase | Signed docs, consent artifacts, links | ["Document Management"] | ["Stored Documents", "Consent Records"] | Possibly | Yes | Yes | TBD | TBD | Mapping reconstruction required
DOM-008 | Payment Profile | Vindicia | Recurring payment profile / token references | ["Payment Portal", "Chase", "PaymentTech"] | ["Recurring Profile", "Tokenized Payment Method"] | Yes | Yes | Yes | TBD | TBD | Key open topic
DOM-009 | Address / Serviceability | Optima / legacy address sources | Customer address, service location | ["UAF", "Serviceability", "Possibly MDM"] | ["Canonical Address", "Eligibility Address"] | Likely | Likely | Yes | TBD | TBD | Pre-population vs migration unresolved
DOM-010 | Usage / Unbilled Usage | Kansas, usage summarization process | Usage events, summaries, unbilled usage | ["New BSS TBD", "Possibly Kenan 7 TBD"] | ["Usage Summary", "Charges Pending"] | Maybe | Unclear | Possibly | TBD | TBD | Bruno mentioned unbilled usage as possible need
DOM-011 | Insurance / Protection | Current assurance-linked flows | Insurance enrollment by IMEI/MSISDN | ["Assurance"] | ["Protection Enrollment"] | Yes, if applicable | Unclear | Yes | TBD | TBD | Same assurance platform may reduce migration need
DOM-012 | Customer Verification Context | Legacy customer identity context | Customer identifiers used for fraud/verification | ["CVT / ECBT", "Experian"] | ["Verification Context"] | Yes, likely during transactions | No clear historical migration stated | Yes | TBD | TBD | Needs coexistence-aware identity handling
DOM-013 | Routing / Coexistence Marker | Legacy + migration control logic | Old/new stack status for customer | ["MML"] | ["Routing / stack-resolution marker"] | Yes | Not classic historical migration | Yes | TBD | TBD | Critical for coexistence

## Issues
Issue ID | Topic | Related Source System(s) | Related Target System(s) | Impact on Mapping | Owner | Status | Notes
ISS-001 | Network-first vs BSS-first strategy | ["Optima", "Altice Labs", "IVR"] | ["MML", "OneView", "Portability", "T-Mobile / target network", "New BSS"] | High | TBD | Open | Valery said decision is needed now
ISS-002 | MML authoritative location | ["IVR / current routing", "legacy customer state"] | ["MML", "MDM", "OneView", "CES", "CVT"] | High | TBD | Open | MDM vs OneView-hosted model unresolved
ISS-003 | Payment profile migration design | ["Vindicia"] | ["Payment Portal", "Chase", "PaymentTech"] | High | TBD | Open | Evaluate copy-in-advance approach
ISS-004 | Document migration method | ["Logical Doc", "Couchbase"] | ["Document Management"] | High | TBD | Open | Mapping reconstruction challenge
ISS-005 | Altice Labs migration scope | ["Altice Labs"] | ["UID / Inventory", "SIM Inventory", "Service Inventory"] | High | TBD | Open | Explicit follow-up needed
ISS-006 | Usage migration scope | ["Kansas", "Nokia Usage App"] | ["New BSS TBD", "Kenan 7 TBD"] | Medium/High | TBD | Open | Historical vs unbilled-only unclear
ISS-007 | Target owner assignment | ["All"] | ["All"] | High | Jose / program leadership TBD | Open | Repeated blocker in discussion
ISS-008 | Dedicated migration PM gap | ["All"] | ["All"] | High | Jose Lopez escalation | Open | To be summarized for Diego/Luciano

## Team
Area | IT Owner | Business Owner | Notes
Overall migration technical orchestration | George Grunwald | TBD | George identified as point person into Dave’s team
Amdocs engineering / legacy source support | Jyotirmaya Pradhan | TBD | Engineering lead from Amdocs
Legacy mobile migration stakeholder | Valery Lev | TBD | Strong strategy/input role
Amdocs migration working focal | Bruno Almeida Araujo | TBD | Supports migration details
Enterprise architecture / target-system walkthrough | Sebastian Leupold | TBD | Helped identify participating systems
Program integration / readiness reporting | Jose Lopez | TBD | Preparing summary to Diego/Luciano
Network migration area | TBD (Sean referenced) | TBD | Sean referenced as network migration lead in discussion